Please enter your name as it appears in Blackboard.
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any features not planned for the current sprint.

If you planned a "full credit" feature for the current sprint but don't complete it, then just update this cell for the next sprint. This will only affect your grade if this feature was *required* to be completed by a specific sprint, and is not.

If you planned a "bonus" or "extreme bonus" feature for the current sprint but don't complete it, and you don't want to use it for the next sprint, just use the Delete key to leave this cell blank. Your "full credit" grade will not be penalized for this decision.
This cell may only contain a valid sprint number - an integer between 1 and the number of sprints in the project. Or it may be left blank (hint: use the Delete key).
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO SHIP.
    "Finished in Sprint 1" means it was delivered at the end of Sprint 1.
    "Finished in Sprint 2" / "Finished in Sprint 3" are the same for those sprints.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
## Product Backlog
Product Name:	CSE1325 Paint					Complete Fields in Green!!!
Team ID:

Name:	Professor Rice
Initials:	GFR
Student ID:

Teaming is not available for this assignment!
Optional teaming may be available in future assignments

	Remaining	Completed (this sprint)
Total Features	23			Total
Sprint 1 Left	14	9		1
Sprint 2 Left	6	8		2
Sprint 3 Left	6	0		3

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
				Sprints
Feature ID	Priority		Step	Planned	Status	As an...	I want to...	So that I can...	Notes
XX	1		2		Finished in Sprint 1	Artist	Exit via x – check for “dirty” bit and prompt to save given new data	Close the window
XFE	2		2		Finished in Sprint 1	Artist	Exit via File > Exit – creating a File > Exit menu item	Close the window independent of the OS
DDL	3		3		Finished in Sprint 1	Artist	Draw discrete lines – click for (x1, y1), drag to (x2, y2)	Create line art
RB	4		4		Finished in Sprint 1	Artist	Draw with rubber bands	More accurately place shapes on the drawing
PC	5		5		Finished in Sprint 1	Artist	Change pen color – use a color selection dialog	Create colorful drawings
PW	6		6		Finished in Sprint 1	Artist	Change pen width – use a text input dialog and atoi	Provide more texture and movement
TB	7		6		Finished in Sprint 1	Artist	Select pen properties from a toolbar	Switch pen properties more quickly
SAV	8		7		Finished in Sprint 1	Artist	Save – write the lines vector to a default filename	Reload, reuse, and share drawings
NEW	9		7		Finished in Sprint 1	Artist	New canvas (vector) – toss drawing (prompt to save) and start new	Start a new drawing without closing the program
OP1	10		7		Finished in Sprint 2	Artist	Open – load the lines vector for the default file	Reload, reuse, and share drawings
SVA	11		7		Finished in Sprint 2	Artist	Save as – write the lines vector to a user-specified file	Manage my drawing files with less work
OPN	12		7		Finished in Sprint 2	Artist	Open – load the lines vector from a user-selected file	Reload, reuse, and share drawings
DCL	13		8		Finished in Sprint 2	Artist	Draw contiguous straight lines – sequence of clicks	Create polygons
DFH	14		9		Finished in Sprint 2	Artist	Draw freehand – hold down the mouse and scribble	Create complex shapes
DSH	15		10		Finished in Sprint 2	Artist	Draw dashed lines in all modes	Make my drawings more interesting and attractive
UNDO	16		11		Finished in Sprint 2	Artist	Undo	Make mistakes without having to start over
FX	17					Artist	Plot single-variable functions	Create technical artwork
DFX	18					Artist	Plot double-variable functions	Create technical artwork
TURT	19					Artist	Run Turtle Graphics file	Create reusable complex shapes
CP	20					Artist	Copy Image	Place my drawings into e.g., Office documents
PAS	21					Artist	Paste Image	Insert drawings from e.g., Gnome Screenshot
EXP	22					Artist	Export to PNG format	Save my drawings in an industry standard format
ABT	23		12		Finished in Sprint 2	Lawyer	Acknowledge license obligations	Avoid litigation
Product Backlog Burn Chart
Sprints
Features Remaining at Start of Sprint

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 17		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 24
Demo on

	Remaining	Completed (this day)
Total Tasks	25
Day 1 Left	16	9
Day 2 Left	13	3
Day 3 Left	13	0
Day 4 Left	7	6
Day 5 Left	0	7
Day 6 Left	0	0
Day 7 Left	0	0

	Feature ID		Description	Status	Notes
			Establish Graph_lib Baseline and refactor in Nim’s Mainwin	Completed Day 1
	XX		Observe signal_delete_event, implementing a dirty bool in Canvas	Completed Day 1
	XFE		Derive a Mainwin class from Gtk::Window for customization	Completed Day 1
	XFE		Create File menu with Quit entry	Completed Day 1
	XFE		Initiate signal_delete_event when File > Quit is selected	Completed Day 1
	DDL		Add a DrawingArea to Canvas	Completed Day 1	Inherited from the baseline
	DDL		Observe mouse clicks in the DrawingArea and create Line shapes	Completed Day 1
	DDL		Add Shape::Draw method	Completed Day 1
	DDL		Override DrawingArea::on_draw and draw the line objects	Completed Day 1	Inherited from the baseline
	PC		Add set_pen_color method to View	Completed Day 2
	PC		Add Pen > Color menu item, display color chooser, and set in View	Completed Day 2
	PC		Add color attribute to Shape	Completed Day 2
	PW		Add set_pen_width method to Canvas	Completed Day 4
	PW		Add Pen > Width menu item	Completed Day 4
	PW		Create custom Set Pen Width dialog, set in Canvas	Completed Day 4
	TB		Enable the toolbar	Completed Day 4	Inherited from baseline
	TB		Add pen color button and connect signal	Completed Day 4
	TB		Add pen width button and connect signal	Completed Day 4
	SAV		Add Line::save to stream	Completed Day 5
	SAV		Add Canvas::save to stream	Completed Day 5
	SAV		Add File > Save to menu	Completed Day 5
	SAV		Add save button to tool bar	Completed Day 5
	NEW		Add Canvas::new	Completed Day 5
	NEW		Add File > New to menu	Completed Day 5
	NEW		Add new button to tool bar	Completed Day 5
Sprint Burn Chart
Tasks
Days

## Sprint 02 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 17		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 24
Demo on

	Remaining	Completed (this day)
Total Tasks	23
Day 1 Left	23	0
Day 2 Left	23	0
Day 3 Left	23	0
Day 4 Left	23	0
Day 5 Left	0	23
Day 6 Left	0	0
Day 7 Left	0	0

	Feature ID		Description	Status	Notes
	OP1		Add Line::Line(input stream)	Completed Day 5
	OP1		Add Canvas::Open(filename)	Completed Day 5
	OP1		Add File > Open, passing default filename	Completed Day 5
	OP1		Add open button to tool bar	Completed Day 5
	SVA		Add Mainwin::on_save_as_click with file chooser dialog	Completed Day 5
	SVA		Add File > Save As to menu	Completed Day 5
	SVA		Save selected filename to view	Completed Day 5
	OPN		Add file chooser dialog to open	Completed Day 5
	DCL		Add Canvas::set_draw_mode with constants	Completed Day 5
	DCL		Add contiguous line drawing to mainwin	Completed Day 5
	DCL		Add Pen > Contiguous and Pen > Segment to menu	Completed Day 5
	DCL		Add contiguous and segment to tool bar	Completed Day 5
	DFH		Add motion notify event handler to View	Completed Day 5
	DFH		Add Pen > Freehand	Completed Day 5
	DFH		Add freehand to tool bar	Completed Day 5
	DSH		Add dash patterns, dash index, and getters / setters to Shape	Completed Day 5
	DSH		Add dash index to Shape	Completed Day 5
	DSH		Update Shape::draw and Canvas::on_draw to use dash settings	Completed Day 5
	DSH		Add Pen > Dash with custom dialog to select dash pattern	Completed Day 5
	UNDO		Add Canvas::undo method	Completed Day 5
	UNDO		Add Edit > Undo	Completed Day 5
	ABT		Add About dialog	Completed Day 5
	ABT		Add Help > About	Completed Day 5
Sprint Burn Chart
Tasks
Days

## Sprint 03 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Oct 17		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 24
Demo on

	Remaining	Completed (this day)
Total Tasks	24
Day 1 Left	24	0
Day 2 Left	24	0
Day 3 Left	24	0
Day 4 Left	24	0
Day 5 Left	24	0
Day 6 Left	24	0
Day 7 Left	24	0

	Feature ID		Description	Status	Notes
	UNDO		Add undo button to tool bar
	FX		Add Function base class
	FX		Add dialog to specify Y function to be plotted
	FX		Add Pen > Function
	FX		Add function button to toolbar
	DFX		Add Dfunction base class
	DFX		Add dialog to specify X function to be plotted
	DFX		Add Pen > Double Function
	DFX		Add double function button to toolbar
	TURT		Add Turtle base class from which programs will be derived
	TURT		Add dialog to specify turtle graphics program as text
	TURT		Add Canvas::new_turtle method to add lines to vector
	TURT		Add Pen > Turtle
	TURT		Add turtle button to toolbar
	CP		Convert DrawingArea (View) to pixmap, then copy to buffer
	CP		Add Edit > Copy
	CP		Add copy to tool bar
	PAS		Add Imager:Line type
	PAS		Accept paste of pixmap
	PAS		Convert pixmap to Imager object and add to vector
	PAS		Add Edit > Paste
	PAS		add paste to tool bar
	EXP		Export pixmap (reused from CP) to PNG file
	EXP		Add File > Export
Sprint Burn Chart
Tasks
Days